## Sheet1
PBI | Est of Time | Tasks | Not Started | In progress | Completed | Names
PBI 1: As an election official I want to be able to run the election with just CSV files. So that the election is more secure and there’s no human error. Acceptance Criteria (conditions that have to be fulfilled to ensure the story is complete): Election will only take CSV files as input. The file can’t be changed or updated. The file must have the header that includes: algorithm type, # of seats, # of candidates, # of ballots, and candidate names. Definition of Done (what is required by the team before sending out for review) Able to run without error and pass all tests. System tests with multiple files inputted are passed. Always refactor so no spaghetti code. Documentation is written for this algorithm using Javadoc. Effort: Small, Medium, Large, Extra Large (estimate of effort and time) OR number of hours needed PBI Author(s) Kongmeng Thao, Elsdon Chang, Cindy Su, Ly Xiong | 2025-01-02 | Write a function in the ballotFileReader to read the header and set the election state variables correctly. | FALSE | FALSE | TRUE | Elsdon
|  | Modify current testing files to have headers | FALSE | FALSE | TRUE | Cindy
|  | Unit test to ensure the new function read header of ballot file properly | FALSE | FALSE | TRUE | Cindy
|  | Documentation | FALSE | FALSE | TRUE | Elsdon
|  | Fix testing configuration so it doesn't run Project1/ tests | FALSE | FALSE | TRUE | Kongmeng Thao
|  | Remove unused InitialInput class | FALSE | FALSE | TRUE | Elsdon Chang
|  | Refactor test case for Plurality don't prompt for input | FALSE | FALSE | TRUE | Kongmeng Thao
|  | Refactor test case for STV to get input from file header | FALSE | TRUE | FALSE | Ly Xiong
PBI 2: As an election official I want to use the municipal voting (MV) algorithm to run elections and be able to find winners and break ties. So that voters can vote for multiple candidates without having to rank them for a less complicated multiple candidate voting. Acceptance Criteria (conditions that have to be fulfilled to ensure the story is complete) The system accepts correct CSV files with MV format. Everything must be done without user input other than the CSV file. Ties for the MV algorithm are broken in an unbiased way. The MV algorithm correctly determines the winner(s) based on the most votes received. Definition of Done (what is required by the team before sending out for review) Documentation is written for this class using Javadoc. Test files are created to handle all edge cases. All system and unit tests are written and passed without manual input. Effort: Small, Medium, Large, Extra Large (estimate of effort and time) OR number of hours needed PBI Author(s) Kongmeng Thao, Elsdon Chang, Cindy Su, Ly Xiong | 2025-05-06 | Write the MV class to count the total votes for each candidate, determine winner (s) who have the most votes, and break tie by randomly select | FALSE | FALSE | TRUE | Ly Xiong
|  | Modify the election class |  | FALSE | TRUE | Ly Xiong
|  | Make test files for MV algorithm | FALSE | FALSE | TRUE | Kongmeng Thao
|  | Unit Test MV election | FALSE | FALSE | TRUE | Kongmeng Thao
|  | System test MV election | FALSE | FALSE | TRUE | Kongmeng Thao
|  | Documentation | FALSE | FALSE | TRUE | Ly Xiong
|  | Make new Ballot Class for MV | FALSE | FALSE | TRUE | Cindy Su
PBI 3: As an election official, I want to be able to import multiple CSV files for both STV, PV, and MV elections. So that I can combine ballots from different voting locations into one election. Acceptance Criteria (conditions that have to be fulfilled to ensure the story is complete) The system accepts multiple valid input files for both STV, PV, and MV formats. All ballots from the files are combined and processed as a single election. Definition of Done (what is required by the team before sending out for review) Documentation is written for this class using Javadoc. Test files are created to handle all edge cases. All system and unit tests are written and passed without manual input. Effort: Small, Medium, Large, Extra Large (estimate of effort and time) OR number of hours needed 2-3 hours PBI Author(s) Kongmeng Thao, Elsdon Chang, Cindy Su, Ly Xiong | 2025-02-03 | Change prompt for input function to take in only files and store the file names in an ArrayList | FALSE | FALSE | TRUE | Elsdon Chang
|  | Change processBallotFile() to iterate over the ArrayList of file names. | FALSE | FALSE | TRUE | Cindy Su
|  | Create testing files for multiple files | FALSE | TRUE | FALSE | Cindy Su
|  | System test to ensure function works properly | FALSE | TRUE | FALSE | Elsdon Chang
|  | Documentation | FALSE | FALSE | TRUE | Cindy Su
PBI 5: As an election official, I want a small report after each run of the voting system, summarizing the outcomes of the election, such as what type of election it was, the number of seats, the number of ballots, and a list of candidate, their number of votes, and the percentage of the vote, and lastly the winner(s). So that I can see the details of the election results and save election information for later use or verification. Acceptance Criteria (conditions that have to be fulfilled to ensure the story is complete) After the election is finished counting ballots, the system outputs(prints) a report to the terminal. The report must include: Election type Number of seats Number of ballots List of candidates Each candidate has a number of votes, and a percentage of the total vote. The winner(s) Definition of Done (what is required by the team before sending out for review) Documentation is written for this class using Javadoc. Test files are created to handle all edge cases. All system and unit tests are written and passed without manual input. Effort: Small, Medium, Large, Extra Large (estimate of effort and time) OR number of hours needed PBI Author(s) Kongmeng Thao, Elsdon Chang, Cindy Su, Ly Xiong | 2 | Add a report function for different algorithm classes to calculate the votes percentage for each candidate and format the report in a readable layout when save | TRUE | FALSE | FALSE | Note: Not needed anymore
|  | Unit test report | TRUE | FALSE | FALSE | Note: Not needed anymore
|  | System test report | TRUE | FALSE | FALSE | Note: Not needed anymore
|  | Documentation | TRUE | FALSE | FALSE | Note: Not needed anymore
PBI 6: As an election official I want the election software to ensure that at least half of the candidates are ranked in an STV ballot and handle invalid ballots by removing them. So that the election result is accurate. Acceptance Criteria (conditions that have to be fulfilled to ensure the story is complete) Any ballots removed due to ranking errors are tracked and listed in a report. The total number of ballots is adjusted whenever a ballot is removed. The software checks that at least half of the candidates are ranked. Definition of Done (what is required by the team before sending out for review) Documentation is written for this class using Javadoc. Test files are created to handle all edge cases. All system and unit tests are written and passed without manual input. Removed ballots are listed in the report. Effort: Small, Medium, Large, Extra Large (estimate of effort and time) OR number of hours needed 2-3 hours PBI Author(s) Kongmeng Thao, Elsdon Chang, Cindy Su, Ly Xiong | 2025-02-03 | Write a function to check if ballots is at least half ranked and use it to ignore invalid ballots in readBallots() in BallotFileReader | TRUE | FALSE | FALSE | Note: Not needed anymore
|  | Invaild ballots are remove and update the number of ballots | TRUE | FALSE | FALSE | Note: Not needed anymore
|  | Account for the removed ballot in the report | TRUE | FALSE | FALSE | Note: Not needed anymore
|  | Write ignored ballots to a file called ignoredBallots.txt | TRUE | FALSE | FALSE | Note: Not needed anymore
|  | System testing | TRUE | FALSE | FALSE | Note: Not needed anymore
|  | Unit testing | TRUE | FALSE | FALSE | Note: Not needed anymore
|  | Documentation | TRUE | FALSE | FALSE | Note: Not needed anymore